## Sheet1
Tasks | Week | Length | Finished | To do
Learning Basic Communication Systems | 1 | 2 | 2 | 0
Studying AWGN and Fading Channels | 3 | 1 | 1 | 0
Researching OFDM System | 4 | 1 | 1 | 0
Relevant Material Reading | 5 | 12 | 8 | 4
Cross-layer Model Design | 5 | 1 | 1 | 0
Problem Formulation | 6 | 1 | 1 | 0
Scheme and Algorithm Optimisation | 7 | 10 | 6 | 4
Subcarrier Allocation (MC and MWC) | 7 | 6 | 6 | 0
Power Allocation (WF and WWF) | 9 | 4 | 4 | 0
Data Scheduling (M-LWDF and PD) | 13 | 4 | 0 | 4
Debugging and Result Obtaining | 17 | 2 | 0 | 2
Complexity and Performance Analysis | 19 | 1 | 0 | 1
Thesis Writing | 17 | 20 | 0 | 20
| 13 | 11